# Forumium: A Web Based Forum Platform for University Student

Objective

Project Date

Start: 11/11/2025
End: 9/1/2026

By the end of January 2026, we aim to release the first beta version of the forum platform to students for X University by hiring a team of 5 software developers with a budget of RM 150,000.

Technical Result 
What to be produced?

Produce a working forum platform with all the requirement following the System Requirement Specification SRS

Specification of final product:

- Login and Logout System

- Change Account Password

- Create Post and Topics

- Search Topics

- Add Comments

- Reply Topics

Work Breakdown Structure Diagram

Activity Table

| No. | Activity Description | Activity | Immediate Predecessor | Activity Time(days) |
| --- | --- | --- | --- | --- |
| 1 | Forum Platform Management and Preparation |  |  | 5 |
| 1.1 | Gather Requirement | A | - | 2 |
| 1.2 | Project Proposal | B | A | 3 |
| 2 | Platform Planning and Design |  |  | 5 |
| 2.1 | Establish the selected requirement and design | C | B | 5 |
| 3 | Platform Development |  |  | 11 |
| 3.1 | Select Technical Framework based on the chosen language | D | B | 2 |
| 3.2 | Coding and Debugging | E | D | 7 |
| 3.3 | Create Content and Post | F | C | 2 |
| 4 | Platform Testing and Rework |  |  | 7 |
| 4.1 | Load Forum Content and Integration | G | F | 2 |
| 4.2 | Test site | H | E, G | 5 |
| 5 | Platform Finalization |  |  | 7 |
| 5.1 | Feedback form end user | I | H | 3 |
| 5.2 | Debug | J | I | 4 |
| 6 | Platform Deployment |  |  | 2 |
| 6.1 | Roll Out and Documentation | K | J | 2 |
| 7 | Agile Sprint |  |  | 12 |
| 7.1 | Creat Backlog from Feedback | L | K | 2 |
| 7.2 | Implement Changes | M | L | 10 |
| 8 | Platform Launch |  |  | 1 |
| 8.1 | Launch Forum Platform | N | M | 1 |

AON Activity on Node

AOA Activity on Arrow

24|24

9

Crictical Path: A-B-C-F-G-H-I-J-K-L-M-N

Milestones

| Milestone | Description | Responsible Personnel |
| --- | --- | --- |
| Project Start | Define scope, objectives, SDLC model and assign roles | Project Manager |
| Requirements Completion | Gather requirements, confirm features, finalize tech stack | Lead Designer + Lead Programmer |
| System Environment Setup | Install server, configure database, install Flarum | Lead Programmer + Entire Team |
| Core Development | Customize UI, implement categories, install extensions | Lead Designer + Entire Team |
| Testing Phase | Perform testing, record bugs and do rework | SQA + SCM |
| Deployment | Deploy forum, finalize server setup | Lead Programmer + Lead Designer |
| Final Documentation & Presentation | Prepare report, user guide, and slide deck | Documetation Manager + Entire Team |

Gantt Chart

Agile Model

Software Metrics

Software metrics are quantitative measurements that are used to evaluate several facets of a software product, the project as a whole and the development process. These metrics offer useful data for assessing the performance, quality, and advancement of software development. Software metrics are crucial since they serve as a gauge for improving software processes. Software process improvement makes use of software metrics to analyze how the organization aims to accomplish the improvement objectives and how the existing process model may be enhanced. The project metrics are being used to monitor any risks, evaluate the project team's control over the quality of the software work products, and analyze the project's current state. We are using the project metrics to assess the status of our project, track potential risks and evaluate the project team’s ability to control the quality of the software work products.

Project metrics consist of several types namely size-oriented metrics, function-oriented metrics, object-oriented metrics, use-case oriented metrics and web engineering project metrics. Both size-oriented and function-oriented metrics will be used in this project. Size-oriented metrics measure project data, cost, and effort depending on the size of software created. The capability that this program will provide is the foundation for function-oriented metrics. It is an indirect metric that makes use of function points (FP), which can be calculated early in the software development process before the actual lines of code are known. FP can be obtained from a software's needs.

Each statistic has benefits and drawbacks of its own. Advantages of using size-oriented metrics are that it is easily calculated, and useful for projects with similar environments whereas the advantages of using function-oriented metrics is that it is language independent and based on data known early in the project. On the other hand, the disadvantages of size-oriented metrics are that it is language and programmer dependent whereas the disadvantages of function-oriented metrics are that it is more difficult to calculate, difficult to collect data and FP has no physical meaning.

Size Oriented Metrics

Web Application Lines of Code: 5400

Database Lines of Code: 6000

Total Lines of Code/Size: 11.4 kLOC

| Project | Effort (person-month) | Cost (RM) | Size(kLOC) | Doc. (pages) | Errors | People |
| --- | --- | --- | --- | --- | --- | --- |
| Forumium - Alpha 1 | 28 | 500,000 | 12.5 | 700 | 88 | 11 |
| Forumium – Beta 2 | 17 | 360,000 | 11.7 | 650 | 73 | 8 |
| Forumium – Gamma 3 | 13 | 210,000 | 11.4 | 620 | 61 | 5 |

| Metrics | Forumium - Alpha 1 | Forumium – Beta 2 | Forumium – Gamma 3 |
| --- | --- | --- | --- |
| Productivity = Size/Effort | 12.5/28 = 0.44 | 11.7/17 = 0.69 | 11.4/13 = 0.88 |
| Quality = Errors / Size | 88/12.5 = 14.4 | 73/11.7 = 6.2 | 61/11.4 = 5.3 |
| Documentation = Pages / Size | 700/12.5 = 56 | 650/11.7 = 55 | 620/11.4 = 54 |

Fuction-Oriented Metrics

The software information domain values have been constructed by our project analysts after

analysing the number of functions based on the parameters listed as the following:

| Parameter | Count | Simple | Average | Complex |
| --- | --- | --- | --- | --- |
| Inputs | 7 | 8 | 10 | 13 |
| Outputs | 14 | 12 | 7 | 10 |
| Inquiries | 8 | 8 | 13 | 9 |
| Files | 11 | 9 | 8 | 12 |
| Interfaces | 6 | 5 | 9 | 7 |

Calculating the raw FP value

|  | Simple | Average | Complex |
| --- | --- | --- | --- |
| Inputs x Count | 8 x 7 = 56 | 10 x 7 = 70 | 13 x 7 = 91 |
| Outputs x Count | 7 x 14 = 98 | 7 x 14 = 98 | 10 x 7 = 70 |
| Inquiries x Count | 8 x 8 = 64 | 13 x 8 = 104 | 9 x 8 = 72 |
| Files x Count | 9 x 11 = 99 | 8 x 11 = 88 | 12 x 11 = 132 |
| Interfaces x Count | 5 x 6 = 30 | 9 x 6 = 54 | 9 x 6 = 54 |
| Raw FP | 347 | 414 | 419 |

Forr each complexity adjustment factor, a rating on a scale of 0 to 5 is given, as shown below:

| Complexity adjustment factors | Rate |
| --- | --- |
| F1: Does the system require reliable backup and recovery? | 5 - Essential |
| F2: Are data communications required? | 4 - Significant |
| F3: Are there distributed processing functions? | 4 - Significant |
| F4: Is performance critical? | 4 - Significant |
| F5: Will the system run in an existing, heavily utilized operational environment? | 3 - Average |
| F6: Does the system require on-line data entry? | 5 - Essential |
| F7: Does the on-line data entry require the input transaction to be built over multiple screens or operations? | 3 - Average |
| F8: Are the master files updated on-line? | 4 - Significant |
| F9: Are the inputs, outputs, files, or inquiries complex? | 5 - Essential |
| F10: Is the internal processing complex? | 3 - Average |
| F11: Is the code designed to be reusable? | 5 - Essential |
| F12: Are conversion and installation included in the design? | 3 - Average |
| F13: Is the system designed for multiple installations in different organizations? | 4 - Sigificant |
| F14: Is the application designed to facilitate change and ease of use by the user? | 4 - Average |
| SUM (CAV) | 56 |

Calculating the FP of each Simple, Average & Complex using the formula below:

FP = Raw FP x [0.65 + (0.01 X CAV)]

- Simple: FP = 347 x [0.65 + (0.01 x 56)] = 419.87

- Average: FP = 414 x [0.65 + (0.01 x 56)] = 500.94

- Complex: FP = 419 x [0.65 + (0.01 x 56)] = 506.99

Calculating the productivity, quality, cost, and documentation of the following projects:

| Project | Effort (person-month) | Cost (RM) | Size(kLOC) | Doc. (pages) | Errors |
| --- | --- | --- | --- | --- | --- |
| Forumium - Alpha 1 | 28 | 500,000 | 12.5 | 700 | 88 |
| Forumium – Beta 2 | 17 | 360,000 | 11.7 | 650 | 73 |
| Forumium – Gamma 3 | 13 | 210,000 | 11.4 | 620 | 61 |

Alpha 1

| Metrics | Simple | Average | Complex |
| --- | --- | --- | --- |
| Productivity | 419.87/28 = 14.99 | 500.94/28 = 17.89 | 506.99/28 = 18.10 |
| Quality | 88/419.87 = 0.21 | 88/500.94 = 0.18 | 88/506.99 = 0.17 |
| Cost | 500k/419.87 = 1190.84 | 500k/500.94 = 998.12 | 500k/506.99 = 986.21 |
| Documetation | 700/419.87 = 1.67 | 700/500.94 = 1.40 | 700/506.99 = 1.38 |

Beta 2

| Metrics | Simple | Average | Complex |
| --- | --- | --- | --- |
| Productivity | 419.87/17 = 24.7 | 500.94/17 = 29.47 | 506.99/17 = 29.82 |
| Quality | 73/419.87 = 0.174 | 73/500.94 = 0.145 | 73/506.99 = 0.14 |
| Cost | 360k/419.87 = 857.41 | 360k/500.94 = 718.65 | 360k/506.99 = 710.07 |
| Documetation | 650/419.87 = 1.54 | 650/500.94 = 1.30 | 650/506.99 = 1.28 |

Gamma 3

| Metrics | Simple | Average | Complex |
| --- | --- | --- | --- |
| Productivity | 419.87/13 = 32.30 | 500.94/13 = 38.53 | 506.99/13 = 38.99 |
| Quality | 61/419.87 = 0.145 | 61/500.94 = 0.12 | 61/506.99 = 0.12 |
| Cost | 210k/419.87 = 500.15 | 210k/500.94 = 419.21 | 210k/506.99 = 414.21 |
| Documetation | 620/419.87 = 1.476 | 620/500.94 = 1.23 | 620/506.99 = 1.22 |

# 7.0 - Project Risk Management

Step 1: Possible risk identification

The risks for our projects can be categorized into several categories namely business risks, technical & technology risks, employee risks, development environment risks and customer risks

Business Risks (BR)

- Effect on Company Revenue

The software will be supplied exclusively to the company and will be charged per customer. This will increase revenue for the company. Profits from this project will be used to compensate the employees.

- Delivery Deadline

The delivery deadline for this project which is 24 October is fairly reasonable given that the scope of the project remains unchanged and no changes made to the initial plan.

- End Users

The targeted end users are the general public ranging from various age groups. Therefore, the web application should be made user friendly.

- Documentation that must be provided for customer

Well written and informative documentation should be prepared for the customer as a manual to operate the web application developed. This is because the customer will be given full access to the database, web application, etc.

- Cost of Late Delivery

Late delivery of the application may result in customer dissatisfaction which may either lower our revenue or provide a choice for customers whether or not to accept the web application which is quite risky.

- Cost of Defective Product Delivery: Unknown

Technical & Technology Risks (TTR)

- Are there specific methods used for software analysis?

There are numerous methods that will be used to track and analyse the software progress regularly. Besides that, there will be frequent tests and reviews done to ensure the software is up to expectations. It is further explained in the Software Quality Assurance and Software Configuration Management document.

- Are there any specific software tools being used?

None confirmed yet.

- Are there metrics to be collected in the project?

Yes, particularly size-oriented metrics and function-oriented metrics

Is the technology something new to the organization?

No, the employees have experience working with the technology needed in this software

project.

- Do the requirements need new algorithms or I/O technology?

None for now as in our planning, this project can be completed with the current

technology available.

- Do the requirements need new analysis, design or testing methods?

None for now.

- Do requirements put excessive performance constraints on the product?

No

Customer Risks (CR)

- Does the customer have a solid idea of what is required?

Yes. In a thorough discussion, both parties mutually agreed to the same idea/concept and it was stated in the Software Requirements Specification of the project.

- Is the customer willing to spend time in formal requirements gathering meetings to identify project scope and participate in technical reviews?

Unknown. No inquiry has been made regarding to this matter.

- Does the customer understand the software process and be familiar with the product area?

Yes, the customer had attended a Software Engineering course and had deployed many web applications in the past.

Development Environment Risks

- Are there any sophisticated software tools to be used in this project?

None for now.

- Does the environment make use of the database or a repository?

Yes, it does.

- Have members of the project team received training in each of the tools?

No software tools are identified to be used for now. However, the members are

well-versed with software tools such as Github, Embold and others

- Is there help available in using the tools if needed?

Yes, there are many resources available online but no software tools are being used

currently in our plan.

Employee Risks (ER)

- Are the best people available?

Yes, the most talented software developers, designers, and programmers are on this

project

- Do the people have the required skills

Yes.

- Are there enough people available for this project?

Yes. A small team has been assembled for this project. This improves communication

efficiency as larger teams may not be able to communicate effectively hence reducing

productivity.

- Are all the staff committed to the work?

Yes, they are full-time employees at Flarum with long-term contracts remaining.

- Are the staff well-trained?

Yes

Step 2: Risk Table

| Risk Summary | Risk Category | Probability | Impact (1–4) | RMMM (Mitigation + Monitoring + Management) |
| --- | --- | --- | --- | --- |
| Slow page load or DB lag | Performance Risk TTR | Medium | 3 | Mitigate: Optimize queries, implement caching. Monitor: Track response times. Manage: Add server resources if needed. |
| Hard to maintain after deployment | Support Risk TTR | Low | 2 | Mitigate: Write documentation, follow clean coding. Monitor: Code reviews. Manage: Assign a support team member. |
| Features not completed on time | Schedule Risk ER | High | 4 | Mitigate: Break tasks smaller, weekly progress checks. Monitor: Gantt chart + daily updates. Manage: Extend deadline or add extra manpower if available. |
| Late Delivery | BR |  | 1 |  |
| End Users Resist System | BR |  | 1 |  |
| Changes in Requirements | CR |  | 1 |  |
| Lack of Database Stability | TTR |  | 3 |  |
| Poor Quality Documentation | BR |  | 2 |  |
| Deviation from Software Engineering Standards | TTR |  | 3 |  |
| Poor Comments in Code | ER |  | 2 |  |
| Extra finance Required | BR |  | 2 |  |

Step 3: Risk Mitigation, Monitoring and Management

Late Delivery

Mitigation

Late delivery may be quite costly to the company in terms of finances and reputation. Therefore, any late delivery would be catastrophic in our point of view. Steps have to be taken for proper delivery of the software product by the deadline. One of the steps we are going to take is to estimate the project scope and set the deadline by assigning tasks to the team while taking into consideration the number of members available for the project including their skills, strengths and weaknesses. It is vital for team members to inform about their progress and address all problems that they have encountered.

Monitoring

A schedule has been established during the planning stage for project monitoring purposes. This schedule will be followed closely by the team and the potential for late delivery is indicated by falling behind schedule.

Management In the worst possible case that the project cannot be completed within the stipulated time, theonly possible solution would be to request an extension from the customerwhich could be detrimental to the company reputation and customer satisfaction & relationship.

End Users Resist System

Mitigation

In efforts of preventing this risk, the web application will be developed with keepingend-users inthe centre of our minds. The ease of use of the UI should be made our top priority.

Monitoring

Various external opinions will be gathered throughout the development process and their

opinions will be further discussed by the developers in the effort of producing the best user

interface possible for the end-users.

Management

In the case that the application failed to be accepted by the end-users, detailed research should becarried out to find reasons for its failure. The results could be used to make amendments to the application and release the new solution.

Changes in Requirements

Mitigation

In efforts to prevent this risk, throughout the project, there will be frequent meetings with the

customer for better understanding between both parties involved. This ensures our product will meet the customer's expectations.

Monitoring

The meeting minutes of each of the meetings held with the customer should be prepared and

managed properly from both sides. Then, both parties should agree to the meeting minutes before the beginning of the next meeting. Through this method, the customers and developers will bewell informed about the project.

Management

If there are any changes in requirements, immediate steps should be taken to solve this problemas quickly and effectively as possible. A meeting should be held between the project team and the customer to rectify this issue.

Lack of Database Stability

Mitigation

The developer who is mainly in charge of the database should always perform error checking.

Upon determining the errors, the issues should be notified to the team and resolved at the

earliest.

Monitoring

Any user who accesses the database should not perform any major modifications without the

supervision of the developer who takes care of the database. At any moment, if an error is

noticed, it should be informed to the team.

Management

If instability is detected with the database, the team should have a meeting to identify the

potential causes and find possible solutions to the issue.

Poor Quality Documentation

Mitigation

The documentation team or manager should constantly be in contact with the developers’ team. In order, to ensure that the documents are developed in a timely manner, the project manager is required to monitor the definition of document standards and mechanisms. Regular meetings should be held regarding the documentation. Any doubts should be clarified instantly. Through these meetings, if a developer finds out if any feature is missing in the documentation, it could be added too after consideration. Besides that, the testing team should do the test using this documentation and let the documentation team know about the quality of the documentation prepared for the software.

Monitoring

The development team and the testing team should always watch out for any topics about the

software which may have not been included.

Management

If poor quality is detected, there should be an attempt made by the entire team to improve the

quality of documentation by adding certain required topics or removing any redundant topics.

Deviation from Software Engineering Standards

Mitigation

It is very unlikely to occur since the team involved in this project is quite experienced and have a thorough understanding of the software engineering standards.

Monitoring

Technical reviews will be held regularly to ensure the documentation and actual project is

consistent with each other. All the documents needed should be completed as accurately as

possible which guarantees the team’s compliance to software engineering standards.

Management

To handle this issue, the project must be modified in a way that it complies with the standards.

Technical reviews can be used to determine how to make the project in line with set standards.

Poor Comments in Code

Mitigation

Certain commenting standards should be established by the lead programmer to ensure good

quality code is produced.

Monitoring

The code should be review and the reviewers will determine if the comments given

for the code is appropriate. This ensures that good quality code is created.

Management

If the code quality is detected to be low, then the programmers should perform the necessary

actions to improve the code. Constant close monitoring of the code will reduce the possibility of poor comments in the code. Programmers could resolve this issue by simply modifying the

comments placed or adding new comments.

Extra Finance Required

Mitigation

In future, due to unforeseen circumstances or improper planning, there may be a need for extra money. As a precautionary measure, there could be a reserve fund allocated for such unexpected scenarios.

Monitoring

The finance team should always monitor the cash flow associated with the project and alert the project team in the event of exceeding the allocated budget.

Management

In the case that extra finance is required, the project manager should have a meeting with the

project sponsor and request extra funds. However, this is very unlikely to happen given that the team have handled few similar projects successfully.

Step 4: Risk Map

| Risk Map |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Level of Likelihood | Almost Certain |  |  |  |  |
|  | Likely |  | TTR3 | BR3 TTR1 ER2 |  |
|  | Possible |  |  |  | BR1 |
|  | Unlikely | ER1 |  | BR4, CR1 | BR2 |
|  | Rare |  | TTR2, TTR4 |  |  |
|  |  | 4- Negligible | 3- Marginal | 2- Critical | 1- Catastrophic |
|  |  | Level of impact |  |  |  |

| Legend |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Risk Rating | Low | Moderate | Significant | High | Extreme |

| Business Risk (BR) |  |  |  |
| --- | --- | --- | --- |
| BR1 | Late Delivery | High | P-Possible, 1-Catastrophic |
| BR2 | End User Resist System | Significant | U-Unlikely, 1-Catastrophic |
| BR3 | Poor Quality Documentation | High | L-Likely, 2-Critical |
| BR4 | Extra Finance Required | Moderate | U-Unlikely, 2-Critical |
| Customer Risk |  |  |  |
| CR1 | Changes in Requirement | Significant | U-Unlikely, 2-Critical |
| Technical and Technology Risk (TTR) |  |  |  |
| TTR1 | Lack of Database Stability | High | Likely, 2-Critical |
| TTR2 | Deviation from Software Engineering Standards | Low | Rare, 3-Marginal |
| TTR3 | Hard to maintain after deployment | Moderate | Likely, 3-Marginal |
| TTR4 | Slow page load or DB lag | Low | Rare, 3-Marginal |
| Employee Risk (ER) |  |  |  |
| ER1 | Poor Comments in Code | Low | U-Unlikely, 4-Negligible |
| ER2 | Features not completed on time | Significant | Likely, 2-Critical |

Risk Profile

| Risk | Likelihood | Impact | Risk Rating | Mitigation Plan |
| --- | --- | --- | --- | --- |
| Business Risk |  |  |  |  |
| BR1 - Late Delivery Scope: Late delivery may be quite costly to the company in terms of finances and reputation. | P-Possible Justification: An inadequate number of team members. Large project job scope. | 1- Catastrophic Justification: Effects on the reputation. Service shortfall incurs a penalty. | High | Estimate the project scope and set the deadline by assigning tasks to the team while taking into consideration the number of members available for the project including their skills, strength and weaknesses. |
| BR2 - End User Resist System Scope: The final product is undesired by the customer. | U-Unlikely Justification: The client signed the agreement and accepted the tender | 1- Catastrophic Justification: This will greatly postpone the application work schedule. | Significant | Development should keep end-users in the centre of our minds. The ease of use of the UI should be made our top priority. |
| BR3 - Poor Quality Documentation Scope: Documentation work, if any, are unrelated to the overall project. | L-Likely Justification: The company prioritises working product rather than proper documentation. Early stages can be ad-hoc. | 2-Critical Justification: Poor documentation will lead to trouble in audit and testing stages. | High | The documentation team will work closely with the developers’ team. Regular meetings held to monitor the definition of documentstandards and mechanisms. |
| BR4 - Extra Finance Required Scope: Change requirements, late deadlines will increase cost of project. | U-Unlikely Justification: The cost budget is planned out according to requirements. The finance team monitors the cash flow. | 2-Critical Justification: Without cash flow, the project schedule will be delayed. | Moderate | As a precautionary measure, there could be a reserve fund allocated for such unexpected scenarios. |
| Customer Risk |  |  |  |  |
| CR1 - Changes in Requirements Scope: Clients may request for huge changes that overhauls the project. | U-Unlikely Justification: Tender project is clearly defined by the client side. | 1-Catastrophic Justification: Sudden changes of requirement increases cost and delays final product launch. | Significant | Frequent meetings held with the customer for clear communication. |
| Technical and Technology Risks |  |  |  |  |
| TTR1 - Lack of Database Stability Scope: Database has to handle occasional user spikes, while not sacrificing its efficiency and speed. | L-Likely Justification: Database deployment requires a backend team, with clear communication with the rest of the developers. | 2-Critical Justification: A web app without the database is as good as a sitting duck. | High | Perform error checking regularly. Upon determining the errors, the issues should be notified to the team and resolved at the earliest. |
| TTR2 - Deviation from Software Engineering Standards Scope: Software Engineering is a discipline that practices the best way to develop software. | R-Rare Justification: The management and developer teams have been well-trained in regards to standards compliances. | 3-Marginal Justification: The project's main concerns are proper documentation and a highly reliable working product. | Low | Have a thorough understanding of the software engineering standards. |
| TTR3 - Hard to maintain after deployment Scope: It specifically affects the engineering team's ability to fix bugs, implement new features, and scale the platform as the user base grows. | Likely Justification: Forums often rely on third-party plugins or rapid prototyping to get features live, leading to "spaghetti code." Its point to Rapid Development Cycles | 3 - Marginal Justification: While maintenance difficulties are frustrating for developers, the immediate impact on the end-user is low. | Moderate | Shift toward a microservices or modular monolith approach. This ensures that the "User Authentication" module is independent of the "Forum Categorization" module. |
| TTR4 - Slow page load or DB lag Scope: Latency experienced by the end-user. It covers front-end rendering JavaScript/CSS weight and back-end bottlenecks, such as unoptimized SQL queries, lack of indexing, or server resource exhaustion during peak traffic. | Rare Justification: For a new platform, the volume of data and concurrent users is typically well within the hardware's capabilities. | 3 - Marginal While a slow site is annoying, it is considered "marginal" because it does not result in data loss or security breaches. Users might experience a "jerkier" interface or wait an extra second for a thread to open, but the core utility of the forum remains intact. | Low | To ensure performance remains high even as the community grows by implementing lazy loading for long forum threads so that only the first few comments load initially, reducing the initial payload. |
| Employee Risks |  |  |  |  |
| ER1 - Poor Comments in Code Scope: The comments in the code poorly explained the functionality enough. | U - Unlikely Justification: The developers practice a standard of commenting. | 4-Negligible Justification: The source code is not the priority of the client. | Low | Lead programmer establishes a commenting standard that will be followed by the rest of the developers. |
| ER2 - Features not completed on time Scope: Involves the product roadmap and the development lifecycle. This includes the design, coding, testing, and deployment phases for specific milestones | L - Likely Justification: Software complexity is often underestimated; unforeseen technical hurdles like integrating a specific API or fixing a complex bug which frequently extend timelines. | 2 - Critical | Significant | Break down large tasks into smaller, manageable two-week sprints. This allows for frequent progress checks and early detection of delays using Agile or Sprig Methodology |

Conclusion

Project Risk Rating: High Risk

(3 High, 2 Significant, 1 Moderate, 2 Low)

Contributing Factors

a) Inadequate number of team members combined with a large project job scope.

b) Company culture prioritizes a working product over proper documentation; early stages tend to be ad-hoc.

c) Database deployment requires a dedicated backend team, necessitating clear communication with all other developers.

Recommendations

a) Estimate the total project scope and establish a realistic deadline by assigning specific tasks to the team while accounting for the current headcount.

b) Integrate the documentation team closely with the developers; hold regular meetings to bridge the gap between code and records.

c) Perform database error checking regularly and resolve any identified issues at the earliest possible stage.

d) Set up a reserved fund as a precautionary financial measure.

Key Areas for Attention

a) Legal Guardrails: Contract T&Cs must include a review of penalty clauses, inclusion of limitation of liability, clear conditions/methodology for penalty imposition, and defined reciprocal responsibilities.

b) Stakeholder Clarity: Define clear roles and responsibilities between the Flarum platform team and the client.

c) Commercial Health: Ensure the profitability and long-term sustainability of the chosen business model.

d) Governance: Maintain effective project management throughout the lifecycle.

e) Oversight: Implement rigorous project progress tracking, frequent reviews, and active monitoring.

Software Cost Estimation and Risk Analysis

Task List includes:

- Set up project environment and development

- Design database and source code

- Implement core features (posting, replying, user accounts)

- Test everything and rework

- Final Deployment

- Time Estimation

| Activity | Immediate Predecessor | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Duration E (days) |
| --- | --- | --- | --- | --- | --- |
| Set up environment | – | 3 | 6 | 10 | 6 |
| Design database | 1 | 6 | 10 | 16 | 10 |
| Implement core features | 2 | 13 | 23 | 32 | 23 |
| Test features | 3 | 3 | 6 | 13 | 7 |
| Deploy project | 4 | 2 | 3 | 7 | 4 |
| Total |  |  |  |  | 50 days |

Impact Level:

1 - Catastrophic 	2 - Critical 		3 - Marginal 		4 - Negligible

For the time estimation for the Risk Analysis focuses on the Development, Testing, and Deployment phases, as these stages carry the highest uncertainty and potential impact to the project schedule.